## Sheet1
Task | Start | End | Duration/ Days | Status
Research & Initial Planning | 2025-11-01 | 2025-11-03 | 2 | Completed
Components Selection | 2025-11-03 | 2025-11-05 | 2 | Completed
Design & Simulate Power Conversion | 2025-11-05 | 2025-11-07 | 2 | Completed
Develop & Test Speed Control System | 2025-11-07 | 2025-11-12 | 5 | Completed
Microcontroller Programming | 2025-11-12 | 2025-11-14 | 2 | Completed
Build, Integrate & Test System | 2025-11-14 | 2025-11-15 | 1 | Circuit Ready
Report | 2025-11-15 | 2025-11-21 | 6 | Ready
Submission | 2025-11-21 | 2025-11-21 | 0 | Pending