## Sheet1
Task | Start | End | Duration/ Days | Status | Reason
Components Selection | 2025-09-15 | 2025-09-21 | 6 | Completed | Completed on time as per plan.
Design & Simulate Power Conversion | 2025-10-01 | 2025-10-14 | 13 | Complete (Delayed) | Extra time needed to fix simulation and output ripple issues.
Develop & Test Speed Control System | 2025-10-15 | 2025-10-28 | 13 | Complete (Delayed) | Slight delay due to PWM tuning for smooth motor operation.
Microcontroller Programming | 2025-10-22 | 2025-10-28 | 6 | Completed | Completed on time as per plan.
Build, Integrate & Test System | 2025-11-01 | 2025-11-14 | 13 | Completed | Due to an overall slight delay faced during the circuit design phase.